## Sheet1 (2)
Feature | Initial Estimate | Day 2 | Day 4 | Day 6 | Day 8 | Day 10 | Day 12 | Day 14 | Hours Left
Abstract | 10
Introduction | 20
Helpful For Society | 5
Tools and Technology used | 5
Dataset | 5
Settting | Start | Day 2 | Day 4 | Day 6 | Day 8 | Day 10 | Day 12 | Day 14
Planned Hours | 45
Actual Hours | 2 weeks
Remaining Effort | 45
Ideal Burndown | 45

## Sheet1
Feature | Initial Estimate | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Hours Left
Categories | 60 | 20 | 8 | 5 | 1 | 5 | 10 | 0 | 1 | 10
Synchronization | 60 | 10 | 5 | 2 | 2 | 5 | 10 | 19 | 2 | 5
Acccounts | 60 | 5 | 8 | 2 | 10 | 5 | 10 | 5 | 10 | 5
Reminders | 60 | 10 | 12 | 2 | 3 | 5 | 10 | 2 | 10 | 6
Settting | Start | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Planned Hours |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Actual Hours |  | 45 | 33 | 11 | 16 | 20 | 40 | 26 | 23
Remaining Effort | 240 | 195 | 162 | 151 | 135 | 115 | 75 | 49 | 26
Ideal Burndown | 240 | 210 | 180 | 150 | 120 | 90 | 60 | 30 | 0